## Project Health
Project Name | Account | Business Unit | Service Line | Region | Delivery Head | Delivery Partner | Client Partner | Project Manager | Status | Start Date | End Date (Planned) | Planned Effort (person-days) | Actual Effort (person-days) | Percent Complete | Last Month RAG | Health | Open Risks | Open Issues | CSAT | Contract Value (USD) | Margin % | Billable Headcount | Utilisation %
S/4HANA Core Migration | Cascade Foods | Consumer | SAP | North America | Anjali Verma | Karthik Menon | David Chen | Priya Nair | On Track | 2025-09-01 | 2026-08-31 | 1200 | 1180 | 58 | Green | Green | 2 | 1 | 4.4 | 2450000 | 24 | 14 | 88
Demand Planning Rollout | Cascade Foods | Consumer | Supply Chain B&E | North America | Anjali Verma | Pooja Deshmukh | David Chen | Rahul Sethi | At Risk | 2025-11-01 | 2026-06-30 | 520 | 610 | 72 | Amber | Red | 6 | 5 | 2.9 | 780000 | 7 | 8 | 94
Trade Promotion Analytics | Cascade Foods | Consumer | Enterprise Platforms | EMEA | Rohan Iyer | Neha Bhatt | Laura Esposito | Sara Khan | On Track | 2026-01-15 | 2026-09-30 | 340 | 300 | 40 | Green | Green | 1 | 0 | 4.6 | 520000 | 28 | 6 | 85
Warehouse Control Tower | Northwind Logistics | Industrial | Supply Chain B&E | North America | Sandeep Kulkarni | Arvind Rajan | Tom Becker | Imran Shaikh | At Risk | 2025-10-01 | 2026-07-31 | 900 | 1010 | 65 | Red | Red | 7 | 6 | 2.6 | 1650000 | 5 | 12 | 96
Fleet Telematics Integration | Northwind Logistics | Industrial | Enterprise Platforms | EMEA | Sandeep Kulkarni | Sameer Qureshi | Tom Becker | Imran Shaikh | On Track | 2025-12-01 | 2026-08-15 | 460 | 440 | 55 | Amber | Green | 2 | 1 | 4.1 | 690000 | 21 | 7 | 87
Transport Cost Optimisation | Northwind Logistics | Industrial | Strategy & Consulting | APAC | Meera Krishnan | Arvind Rajan | Aisha Rahman | Wei Lim | On Track | 2026-02-01 | 2026-07-31 | 280 | 270 | 38 | Green | Green | 1 | 1 | 4.3 | 410000 | 30 | 5 | 82
SAP EWM Implementation | Meridian Auto | Industrial | SAP | EMEA | Sandeep Kulkarni | Pooja Deshmukh | Marcus Hale | Stefan Bauer | At Risk | 2025-08-15 | 2026-06-30 | 1050 | 1140 | 80 | Amber | Amber | 4 | 3 | 3.4 | 1980000 | 12 | 15 | 91
Supplier Portal Build | Meridian Auto | Industrial | Enterprise Platforms | EMEA | Rohan Iyer | Neha Bhatt | Marcus Hale | Stefan Bauer | On Track | 2025-11-15 | 2026-09-01 | 520 | 500 | 50 | Green | Green | 2 | 1 | 4.2 | 740000 | 23 | 8 | 86
Plant Maintenance Analytics | Meridian Auto | Industrial | Industrial Solutions | APAC | Meera Krishnan | Arvind Rajan | Aisha Rahman | Wei Lim | On Track | 2026-01-05 | 2026-08-31 | 360 | 350 | 44 | Green | Green | 1 | 0 | 4.5 | 480000 | 27 | 6 | 84
Omnichannel Order Mgmt | Apex Retail | Consumer | Enterprise Platforms | North America | Anjali Verma | Karthik Menon | David Chen | Megan Foster | At Risk | 2025-10-15 | 2026-07-15 | 780 | 860 | 68 | Green | Amber | 5 | 4 | 3.2 | 1320000 | 10 | 11 | 93
Store Replenishment AI | Apex Retail | Consumer | Supply Chain B&E | North America | Anjali Verma | Pooja Deshmukh | David Chen | Megan Foster | On Track | 2026-02-15 | 2026-10-31 | 420 | 400 | 30 | Amber | Green | 2 | 1 | 4 | 560000 | 22 | 7 | 83
POS Modernisation | Apex Retail | Technology | SAP | EMEA | Rohan Iyer | Sameer Qureshi | Laura Esposito | Sara Khan | On Track | 2025-09-15 | 2026-08-01 | 640 | 620 | 60 | Green | Green | 2 | 2 | 4.3 | 910000 | 25 | 9 | 88
Merchandising Data Platform | Apex Retail | Technology | Enterprise Platforms | APAC | Vivek Saxena | Arvind Rajan | Aisha Rahman | Wei Lim | On Track | 2026-01-20 | 2026-09-30 | 300 | 290 | 35 | Green | Green | 1 | 0 | 4.4 | 430000 | 29 | 5 | 81
Cold Chain Visibility | Helios Pharma | Consumer | Supply Chain B&E | EMEA | Sandeep Kulkarni | Neha Bhatt | Laura Esposito | Daniel Roth | At Risk | 2025-11-01 | 2026-06-15 | 580 | 680 | 75 | Red | Red | 8 | 7 | 2.4 | 1240000 | 4 | 10 | 97
Serialisation Compliance | Helios Pharma | Consumer | SAP | North America | Anjali Verma | Karthik Menon | David Chen | Daniel Roth | On Track | 2025-12-15 | 2026-09-15 | 720 | 700 | 52 | Amber | Amber | 3 | 2 | 3.6 | 1080000 | 16 | 10 | 90
Clinical Supply Forecasting | Helios Pharma | Growth Markets | Strategy & Consulting | APAC | Meera Krishnan | Arvind Rajan | Aisha Rahman | Hiro Tanaka | On Track | 2026-02-01 | 2026-10-15 | 260 | 250 | 28 | Green | Green | 1 | 1 | 4.5 | 390000 | 31 | 4 | 80
Procurement Analytics Hub | Cascade Foods | Growth Markets | Strategy & Consulting | APAC | Vivek Saxena | Sameer Qureshi | Aisha Rahman | Hiro Tanaka | On Track | 2026-01-10 | 2026-08-31 | 310 | 300 | 42 | Green | Green | 1 | 0 | 4.2 | 450000 | 28 | 5 | 82
Master Data Governance | Meridian Auto | Technology | SAP | North America | Vivek Saxena | Karthik Menon | Tom Becker | Megan Foster | On Track | 2025-10-01 | 2026-07-31 | 540 | 560 | 62 | Amber | Amber | 3 | 2 | 3.7 | 820000 | 15 | 8 | 89
Network Design Study | Northwind Logistics | Growth Markets | Strategy & Consulting | EMEA | Meera Krishnan | Pooja Deshmukh | Laura Esposito | Stefan Bauer | On Track | 2026-02-20 | 2026-07-01 | 180 | 170 | 33 | Green | Green | 0 | 0 | 4.6 | 260000 | 33 | 3 | 79
Returns Optimisation | Apex Retail | Industrial | Industrial Solutions | North America | Sandeep Kulkarni | Arvind Rajan | David Chen | Imran Shaikh | On Track | 2026-01-02 | 2026-09-01 | 400 | 390 | 47 | Green | Green | 2 | 1 | 4.1 | 610000 | 24 | 7 | 85